## Home
44886 | 21-Nov-22 | Today 21-Nov-22
This Report Is Owned By: www.chartenia.com
Today 21-Nov-22
|  |  |  | Project Name |  |  | Building Best Project
|  |  |  | Report Date |  |  | 2022-10-01
|  |  |  | Cut-Off Date |  |  | 2022-10-01
|  |  |  | Prepared By |  |  | Chartenia Project Control
|  |  |  | Company Name |  |  | Chartenia Project Control
|  |  |  | Revesion No |  |  | Rev.00
Warning: This Document belongs to chartenia, LLC. Purchasing this document does not mean that the buyer can take the ownership of the design, formulas, and the ideas included in this document as they will remain under the sole ownership of Chartenia, LLC. The user of this document will not attempt to waive any of Chartenia's rights by taking the ownership of this document, give for free, resell to others, or republishing it under his/her name, or changing any of the document's access security rights. This document is copyrighted to Chartenia, LLC. If you have any questions, please contact us: www.chartenia.com info@chartenia.com
This Report Is Owned By: www.chartenia.com
[5 empty] | Verification | 1 | This Report Is Owned By: www.chartenia.com

## Dashboard
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67
Building Best Project
  Progress S-Curve (Planned Vs Actual)
70%
70%
60%
% Planned
37.50%
% Actual
30.24%
% Variance
-7.26%
  Work Package Performance.
% Elapsed Time
50%
% Remaining Time
50%
% Total Delay
22%
Please Print In PDF so you can get the fit format of the Dashboard
To know more about our construction dashboards, please visit
www.chartenia.com
This Dashboard is under a copyright by chartenia

## Time Schedule Input
Sr. | Items | Planned Start | Pl. Finish | A/F Start | A/F Finish | % Planned | % Planned Balance | % Actual | % Actual Balance | Data Date | Original Duration | Elapsed Duration | Remaining Duration | Delay | % Elapsed Time | % Remaining Time | % Time Delay | % Variance | SPI | Clock | Needle
1 | Project Overall | 2022-01-01 | 2023-06-30 | 2022-12-30 | 2023-10-30 | 34.81% | 65.19% | 24.24% | 75.76% | 2022-10-01 | 545 | 273 | 272 | 122 | 50.09% | 49.91% | 22.39% | -10.58% | 0.69623 | 25% | 50.09%
2 | Engineering |  |  |  |  | 80% | 20% | 70% | 30% | 2022-10-01 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | -10% | 0.875 | 25% | 1%
3 | Procurement |  |  |  |  | 80% | 20% | 70% | 30% | 2022-10-01 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | -10% | 0.875 | 25% | 48.91%
4 | Construction |  |  |  |  | 70% | 30% | 60% | 40% | 2022-10-01 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | -10% | 0.85714 | 25%
5 | Main Package 1 |  |  |  |  | 100% | 0% | 100% | 0% | 2022-10-01 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 0% | 1
6 | Main Package 2 |  |  |  |  | 85% | 15% | 78% | 22% | 2022-10-01 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | -7% | 0.91765
7 | Main Package 3 |  |  |  |  | 67% | 33% | 53% | 47% | 2022-10-01 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | -14% | 0.79104
8 | Main Package 4 |  |  |  |  | 50% | 50% | 42% | 58% | 2022-10-01 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | -8% | 0.84
9 | Main Package 5 |  |  |  |  | 40% | 60% | 31% | 69% | 2022-10-01 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | -9% | 0.775
10 | Main Package 6 |  |  |  |  | 0% | 100% | 0% | 100% | 2022-10-01 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0!
Note
you only need to fill the green shaded cells and the rest of the table will be filled automatically.

## S-Curve Data Input Overall
Months | Monthly Planned Value | Monthly Actual Value | Cumulative Planned Value | Cumulative Actual Value | Schedule Variance | SPI | % Monthly Planned Value | % Monthly Actual Value | % Planned | % Actual | % Mothly Schedule Variance | % Cumulative Schedule Variance | Elapsed Months | Months of SPI | SPI 4 M LB | % Planned | % planned Remaining | % Actual | % Actual Remaining | % Variance 4MLB | % Monthly Planned | %Monthly Actual
2022-01-01 | 3201 | 3000 | 3201 | 3000 | -201 | 0.93721 | 0.4001% | 0.375% | 0.4001% | 0.375% | -0.02513% | -0.02512% | 2022-01-01 | 2022-07-01 | 0.43879 | 27.78% | 72.22% | 12.19% | 87.81% | -15.59% | 5.737% | 3.75%
2022-02-01 | 17800 | 3500 | 21001 | 6500 | -14501 | 0.30951 | 2.225% | 0.4375% | 2.625% | 0.8125% | -1.787% | -1.813% | 2022-02-01 | 2022-08-01 | 0.55775 | 31.6% | 68.4% | 17.62% | 82.38% | -13.98% | 3.825% | 5.438%
2022-03-01 | 22900 | 10000 | 43901 | 16500 | -27401 | 0.37585 | 2.863% | 1.25% | 5.488% | 2.062% | -1.613% | -3.425% | 2022-03-01 | 2022-09-01 | 0.69623 | 34.81% | 65.19% | 24.24% | 75.76% | -10.58% | 3.212% | 6.613%
2022-04-01 | 30700 | 9000 | 74601 | 25500 | -49101 | 0.34182 | 3.837% | 1.125% | 9.325% | 3.188% | -2.712% | -6.138% | 2022-04-01 | 2022-10-01 | 0.80633 | 37.5% | 62.5% | 30.24% | 69.76% | -7.263% | 2.688% | 6%
2022-05-01 | 45800 | 20000 | 120401 | 45500 | -74901 | 0.3779 | 5.725% | 2.5% | 15.05% | 5.688% | -3.225% | -9.363% | 2022-05-01
2022-06-01 | 55900 | 22000 | 176301 | 67500 | -108801 | 0.38287 | 6.988% | 2.75% | 22.04% | 8.438% | -4.238% | -13.6% | 2022-06-01
2022-07-01 | 45900 | 30000 | 222201 | 97500 | -124701 | 0.43879 | 5.737% | 3.75% | 27.78% | 12.19% | -1.988% | -15.59% | 2022-07-01
2022-08-01 | 30600 | 43500 | 252801 | 141000 | -111801 | 0.55775 | 3.825% | 5.438% | 31.6% | 17.62% | 1.613% | -13.98% | 2022-08-01
2022-09-01 | 25700 | 52900 | 278501 | 193900 | -84601 | 0.69623 | 3.212% | 6.613% | 34.81% | 24.24% | 3.4% | -10.58% | 2022-09-01
2022-10-01 | 21500 | 48000 | 300001 | 241900 | -58101 | 0.80633 | 2.688% | 6% | 37.5% | 30.24% | 3.312% | -7.263% | 2022-10-01
2022-11-01 | 18900 | 35000 | 318901 | 276900 | -42001 | 0.86829 | 2.362% | 4.375% | 39.86% | 34.61% | 2.013% | -5.25% | 2022-11-01
2022-12-01 | 25200 | 20000 | 344101 | 296900 | -47201 | 0.86283 | 3.15% | 2.5% | 43.01% | 37.11% | -0.65% | -5.9% | 2022-12-01
2023-01-01 | 33800 | 18900 | 377901 | 315800 | -62101 | 0.83567 | 4.225% | 2.362% | 47.24% | 39.48% | -1.862% | -7.763% | 2023-01-01
2023-02-01 | 40900 | 27600 | 418801 | 343400 | -75401 | 0.81996 | 5.112% | 3.45% | 52.35% | 42.93% | -1.663% | -9.425% | 2023-02-01
2023-03-01 | 49800 | 35900 | 468601 | 379300 | -89301 | 0.80943 | 6.225% | 4.487% | 58.58% | 47.41% | -1.738% | -11.16% | 2023-03-01
2023-04-01 | 65800 | 48800 | 534401 | 428100 | -106301 | 0.80108 | 8.225% | 6.1% | 66.8% | 53.51% | -2.125% | -13.29% | 2023-04-01
2023-05-01 | 70200 | 55700 | 604601 | 483800 | -120801 | 0.8002 | 8.775% | 6.963% | 75.58% | 60.48% | -1.812% | -15.1% | 2023-05-01
2023-06-01 | 50699 | 68600 | 655300 | 552400 | -102900 | 0.84297 | 6.337% | 8.575% | 81.91% | 69.05% | 2.238% | -12.86% | 2023-06-01
2023-07-01 | 39800 | 60500 | 695100 | 612900 | -82200 | 0.88174 | 4.975% | 7.562% | 86.89% | 76.61% | 2.587% | -10.27% | 2023-07-01
2023-08-01 | 37800 | 55000 | 732900 | 667900 | -65000 | 0.91131 | 4.725% | 6.875% | 91.61% | 83.49% | 2.15% | -8.125% | 2023-08-01
2023-09-01 | 26100 | 45000 | 759000 | 712900 | -46100 | 0.93926 | 3.263% | 5.625% | 94.88% | 89.11% | 2.362% | -5.762% | 2023-09-01
2023-10-01 | 15500 | 35000 | 774500 | 747900 | -26600 | 0.96566 | 1.938% | 4.375% | 96.81% | 93.49% | 2.438% | -3.325% | 2023-10-01
2023-11-01 | 13900 | 25000 | 788400 | 772900 | -15500 | 0.98034 | 1.738% | 3.125% | 98.55% | 96.61% | 1.387% | -1.938% | 2023-11-01
2023-12-01 | 11600 | 12800 | 800000 | 785700 | -14300 | 0.98213 | 1.45% | 1.6% | 100% | 98.21% | 0.15% | -1.788% | 2023-12-01
2024-01-01 | 0 | 7900 | 800000 | 793600 | -6400 | 1 | 0% | 0.9875% | 100% | 99.2% | 0.9875% | -0.8% | 2024-01-01
2024-02-01 | 0 | 4400 | 800000 | 798000 | -2000 | 1 | 0% | 0.55% | 100% | 99.75% | 0.55% | -0.25% | 2024-02-01
2024-03-01 | 0 | 2000 | 800000 | 800000 | 0 | 1 | 0% | 0.25% | 100% | 100% | 0.25% | 0% | 2024-03-01
2024-04-01 | 0 |  | 800000 | #N/A | #N/A | 1 | 0% | #N/A | 100% | #N/A | 0% | #N/A | #N/A
Note
This sheet is allocated to input the perfromance numbers. Whether you are using Progress Units, Man-hours numbers or earned value numbers, you only need to fill the green shaded cells (Planned & Actual) and the rest of the cells and the charts will be updated automatically.
In case you find inconsistency, please contact
info@chartenia.com