## Home
44886 | 21-Nov-22 | Today 21-Nov-22
This Report Is Owned By: www.chartenia.com
Today 21-Nov-22
|  |  |  | Project Name |  |  | Building Best Project
|  |  |  | Report Date |  |  | 2022-01-01
|  |  |  | Cut-Off Date |  |  | 2022-01-01
|  |  |  | Prepared By |  |  | Chartenia Project Control
|  |  |  | Company Name |  |  | Chartenia Project Control
|  |  |  | Revesion No |  |  | Rev.00
Warning: This Document belongs to chartenia, LLC. Purchasing this document does not mean that the buyer can take the ownership of the design, formulas, and the ideas included in this document as they will remain under the sole ownership of Chartenia, LLC. The user of this document will not attempt to waive any of Chartenia's rights by taking the ownership of this document, give for free, resell to others, or republishing it under his/her name, or changing any of the document's access security rights. This document is copyrighted to Chartenia, LLC. If you have any questions, please contact us: www.chartenia.com info@chartenia.com
This Report Is Owned By: www.chartenia.com
[5 empty] | Verification | 1 | This Report Is Owned By: www.chartenia.com

## Time Schedule Input
Sr. | Items | Planned Start | Pl. Finish | A/F Start | A/F Finish | % Planned | % Planned Balance | % Actual | % Actual Balance | Data Date | Original Duration | Elapsed Duration | Remaining Duration | Delay | % Elapsed Time | % Remaining Time | % Time Delay | % Variance | SPI | Clock | Needle
1 | Project Overall | 2021-01-01 | 2023-03-30 | 2021-01-01 | 2023-05-30 | 60% | 40% | 40% | 60% | 2022-01-01 | 818 | 365 | 453 | 61 | 44.62% | 55.38% | 7.457% | -20% | 0.66667 | 25% | 44.62%
2 | Engineering | 2021-01-01 | 2021-08-01 | 2021-01-01 | 2021-12-01 | 100% | 0% | 90% | 10% | 2022-01-01 | 212 | 212 | 0 | 122 | 100% | 0% | 57.55% | -10% | 0.9 | 25% | 1%
3 | Procurement | 2021-01-03 | 2021-12-01 | 2021-03-04 | 2022-02-28 | 100% | 0% | 60% | 40% | 2022-01-01 | 332 | 332 | 0 | 89 | 100% | 0% | 26.81% | -40% | 0.6 | 25% | 54.38%
4 | Construction | 2021-04-01 | 2023-03-30 | 2021-05-01 | 2023-05-30 | 70% | 30% | 50% | 50% | 2022-01-01 | 728 | 275 | 453 | 61 | 37.77% | 62.23% | 8.379% | -20% | 0.71429 | 25%
5 | Main Package 1 | 2021-04-01 | 2021-12-01 | 2021-05-01 | 2022-02-02 | 100% | 0% | 100% | 0% | 2022-01-01 | 244 | 244 | 0 | 63 | 100% | 0% | 25.82% | 0% | 1
6 | Main Package 2 | 2021-06-30 | 2022-03-01 | 2021-07-30 | 2022-05-03 | 80% | 20% | 60% | 40% | 2022-01-01 | 244 | 185 | 59 | 63 | 75.82% | 24.18% | 25.82% | -20% | 0.75
7 | Main Package 3 | 2021-09-28 | 2022-05-30 | 1028-21 | 2022-08-15 | 50% | 50% | 45% | 55% | 2022-01-01 | 244 | 95 | 149 | 77 | 38.93% | 61.07% | 31.56% | -5% | 0.9
8 | Main Package 4 | 2021-12-27 | 2022-08-28 | 2022-01-26 | 2022-10-15 | 10% | 90% | 2% | 98% | 2022-01-01 | 244 | 5 | 239 | 48 | 2.049% | 97.95% | 19.67% | -8% | 0.2
9 | Main Package 5 | 2022-03-27 | 2022-11-26 | 2022-04-26 | 2023-01-28 | 0% | 100% | 0% | 100% | 2022-01-01 | 244 | 0 | 244 | 63 | 0% | 100% | 25.82% | 0% | #DIV/0!
10 | Main Package 6 | 2022-06-25 | 2023-03-30 | 2022-07-25 | 2023-05-30 | 0% | 100% | 0% | 100% | 2022-01-01 | 278 | 0 | 278 | 61 | 0% | 100% | 21.94% | 0% | #DIV/0!
Note
you only need to fill the green shaded cells and the rest of the table will be filled automatically.

## Dashboard
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67
Building Best Project
% Elapsed Time
55%
% Remaining Time
45%
% Total Delay
7%
  Project Time Update
  Work Package Performance.
Project Calendar
Project Performance
% Planned
60%
% Actual
40%
% Variance
-20%
Please Print In PDF so you can get the fit format of the Dashboard
To know more about our construction dashboards, please visit
www.chartenia.com
This Dashboard is under a copyright by chartenia